## Slide 1
Scrum Product Owner
June 17, 2020
Michael Gaffney (670800)

## Slide 2: Purpose
The intent of this short session is to review the role of the Product Owner in Scrum and to discuss a number of real-world-style situations a Product Owner may encounter.
This session is not intended as preparation for any Product Owner certification.

## Slide 3: Outline
Quick review/overview of Scrum
The role of the Product Owner in relation to the events and artifacts of Scrum.
Discussion of situations a Product Owner may find herself in and appropriate responses to those situations.

## Slide 4
Scrum Quick Review

## Slide 5: Scrum
Scrum is a framework for developing products using an empirical process
Scrum specifies
  Pillars and Values
  Roles
  Events
  Artifacts

## Slide 6: Scrum Pillars and Values
Pillars of empirical process control
  Transparency
  Inspection
  Adaptation

## Slide 7: Scrum Values
Added in 2017 to emphasize the behaviors and attitudes needed for the pillars to be most effective
  Commitment
  Courage
  Focus
  Openness
  Respect

## Slide 8: Scrum Roles
Scrum specifies 3 co-equal roles in a Scrum team
  The Scrum Master
    Serves as expert and guide on the framework
  The Product Owner
  The Development Team
    Develops the product
      Self-organizing, self-directing, collectively responsible

## Slide 9: Scrum Events
The Sprint
  Sprint Planning
  Development period
    Daily Scrum
  Sprint Review
  Spring Retrospective
Each Sprint

## Slide 10: Scrum Artifacts
Product Backlog
  Work Items
  Estimates
Sprint Backlog
  Sprint Plan
  Work Items
  Work Estimates
Sprint Goal
  Simple statement of the outcome of the Sprint

## Slide 11: Scrum Artifacts
Definition of Done
  Criteria under which everything from a work item to the entire increment are to be considered finished
Definition of Ready (optional – not part of guide)
  Criteria under which Product Backlog items are ready to be included in a Sprint
Increment
  Product as it stands at the end of a Sprint
  Production-ready, potentially releasable

## Slide 12
The Product Owner

## Slide 13: Product Owner
The Product Owner is a single person
  Not a committee
  Not a primary/secondary list of people
The Product Owner is part of the team
  They won't generally sit with the team, but must be available to contribute on short notice
The Product Owner is required

## Slide 14: Product Owner Qualifications
Understanding of her role OR trust in the guidance of a qualified Scrum Master
Understanding of the product under development
Understanding of the business
  Key stakeholders
  Key drivers of value

## Slide 15: Product Owner Role
The Product Owner is responsible for ensuring that the Development Team is always producing the most value they can.
  Interfaces with the rest of the stakeholders to track changing needs
  Manages the Product Backlog
  Is the final authority on the project requirements
  Requires the trust and respect of the entire organization

## Slide 16: Managing the Product Backlog
The Product Owner's primary responsibility is the Product Backlog
  Ensuring the backlog items are clear and correct representations of the requirements
  Ensuring that the highest value items are first on the backlog
  Ensuring that the Development Team understands the backlog items
  Ensuring that the backlog is transparent to all interested parties in the organization.

## Slide 17: Managing the Product Backlog
No one can change the product backlog other than the Product Owner.
  Not her immediate superior
  Not the CIO
  Not the AVP over the group the product is being made for
  Not the Scrum Master or Development team (although naturally they consult with the Product Owner more regularly than others).

## Slide 18: Product Owner as Arbiter
The Product Owner is responsible for resolving conflicting needs and desires
  What gets on the backlog
  What has more value than what
  How specific requirements get expressed
A trusted, respected Product Owner eliminates decision paralysis and ensures high team productivity.

## Slide 19: Product Owner Services
To the Development Team
  Sharing vision
  Clarifying Product Backlog items
  Communicating stakeholder input (and buffering the Development Team from direct stakeholder interaction)
  Keeping the Product Backlog up to date

## Slide 20: Product Owner Services
To the Scrum Master
  Timely, open, and transparent communication regarding real or potential impediments arising from outside the team
  Advocating for the Scrum Master's importance among stakeholders (with whom the Product Owner often has more established relationships)

## Slide 21
The Product Backlog

## Slide 22: Product Backlog
Repository of all outstanding work to be done on the product for the product's entire life
Never complete as long as the product is active
  Requirements get added, removed, and changed
  Enhancements get added
  Bug fixed get added
  Low-priority items may linger for years and then be brought to the top

## Slide 23: Product Backlog
There are three key components of the Product Backlog
User Stories/enhancements/fixes
The prioritization of items
The effort estimation of items

## Slide 24: User Stories
Represent a particular user interaction with the product
Collectively represent the entire product
Are written by the stakeholders and managed by the Product Owner
Are initially very simple
  "A customer can view their account information"

## Slide 25: User Stories
User stories are refined and clarified as they become close to being selected for a sprint
The Product Owner provides clarification on them based on stakeholder input and questions from the development team
Stories are not clarified while low priority due to the likelihood of their meaning changing or their being dropped or replaced.

## Slide 26: Epics
Stories that represent complex interactions with the system that may be difficult to complete within a single sprint are called Epics
  Part of refining epics is creating smaller story components of them that can be estimated and selected for inclusion in a sprint independently
  Epics, like sprints, are only refined as they become high priority.

## Slide 27: Prioritizing the Product Backlog
The Product Owner is responsible for prioritizing the product backlog.
  Prioritization is done solely on the basis of the value stories have to the business
    Not effort (do not prioritize "quick" items for the illusion of progress)
    Not relevance to other high-priority items
      Don't prioritize an item from module A just because module A has a lot of work done on it

## Slide 28: Prioritizing the Product Backlog
The Product Backlog is prioritized as needed
  Like everything else, priorities now may be different from ones in 6 months
  Prioritize a few months worth of items – roughly 2-4 sprints' worth
  As items get removed, determine what needs to be added, review what's already at the top, and shuffle as needed

## Slide 29: Managing the Product Backlog
The Product Owner can change the contents or priority of the Product Backlog at any time.
The only restriction is that there must be time for the Development Team to provide any needed estimates of effort before items are pulled off for development.

## Slide 30
Sprint Planning

## Slide 31: Sprint Planning
Entire Scrum Team participates
Produces two artifacts
  The Sprint Backlog
  The Sprint Goal

## Slide 32: PO Role in the Sprint Planning Meeting
The Product Owner is prepared to discuss, in detail, roughly two sprints worth of priority Product Backlog Items
In the context of these available items, the Product Owner and Development team collaboratively decide on the Sprint Goal
The Product Owner provides support as the Development Team plans the Sprint

## Slide 33: The Sprint Goal
A one-two sentence statement of what this sprint will accomplish
The guiding statement for managing the sprint
The standard against which the success of the sprint is measured
Is understandable by outside stakeholders

## Slide 34
Daily Scrum

## Slide 35: PO Role in the Daily Scrum
Product Owner has no role in the daily Scrum
Might be invited if input is needed, but this is more appropriate to a separate meeting.

## Slide 36
Development Period

## Slide 37: PO Role in the Development Period
Availability to provide clarification to requirements
Interface (and buffer) between developers and stakeholders
Collaborate with Development team if work is over- or underestimated
Determine if a Sprint needs to be cancelled

## Slide 38: Mis-estimated Sprint
Over- and underestimating refer to the amount of work required for the backlog items
  Overestimated Sprint doesn't have enough work
  Underestimated Sprint has too much work
Success for a Sprint is based on meeting the Sprint Goal.

## Slide 39: Overestimated Sprint
The Development Team may request that the Product Owner collaborate with them to add more items from the Product Backlog to the Sprint
They may choose to engage in other work.

## Slide 40: Underestimated Sprint – Still Successful
Items can be removed from a Sprint and it will still be successful if the Sprint Goal is reached.
  This is the Product Owner's decision, based on the progress of the Sprint and Development team input
Definition of Done cannot be changed
Duration of Sprint cannot be increased

## Slide 41: Underestimated Sprint – failed
Product Owner and Development team collaborate on
  A modified Sprint Goal
  A corresponding reduced set of backlog items
    That will still meet the Definition of Done
    That will still result in a production-ready, potentially releasable increment
This is likely in early sprints

## Slide 42: Cancelled Sprint
Rarely, sprints are cancelled
  Product Owner's call
  Mostly when the Sprint Goal becomes irrelevant
    Would need to get there from highest priority in less than a month
  Done work is reviewed for relevance and possibly accepted into an increment
  Incomplete but relevant work is placed back on the Product Backlog

## Slide 43
Sprint Review

## Slide 44: Sprint Review
Attended by entire Scrum team and key stakeholders
Intended to share the results of the sprint with stakeholders and to get feedback from stakeholders on the business and product
Results in a revised Product Backlog

## Slide 45: Sprint Review Activities
Results of the sprint are presented to the stakeholders
  What is Done (and not Done) with respect to the Goal
  What went well during the sprint and what had to be overcome
  The updated increment with Done items is demonstrated by the development team and stakeholder questions are answered

## Slide 46: Sprint Review Activities
Product Backlog is collaborated on
  Product Owner leads this discussion
  Entire group is involved
  Stakeholders provide marketplace or business goal updates impacting value
  Timelines, budgets, current velocity and anticipated release are discussed
  The contents and prioritization of the Product Backlog is updated

## Slide 47
Sprint Retrospective

## Slide 48: Sprint Retrospective
A time-boxed three-hour (for a one-month sprint) meeting
  Attended by the entire Scrum team
  Intended to improve the working of the Scrum team
  Is the period of the Sprint that most requires adherence to the Scrum Values
  Focuses forward on improvement

## Slide 49: Activities of the Sprint Retrospective
Inspect the previous sprint
  Processes
  Tools
  People..
  Relationships...
This can be a hard meeting
This is an essential meeting

## Slide 50: Activities of the Sprint Retrospective
Identify and order major items
  That went well
  That need improvement
Create a plan to reinforce what worked well and correct (or at least mitigate) what did not.
Do not neglect to address what went well or not so well in this meeting

## Slide 51
Artifacts and the Product Owner

## Slide 52: Artifacts
Product Backlog
  Product Owner owns this entirely
Sprint Backlog
  Development Team owns this
  Product Owner consults on it
Sprint Goal
  Development Team and Product Owner jointly own this

## Slide 53: Artifacts, cont.
Definition of Done
  May be organizational
  Otherwise, defined by Development Team and approved by Product Owner
Increment
  Developed by development team
  Accepted by Product Owner based on compliance with Definition of Done

## Slide 54
Situations

## Slide 55: Enthusiastic Development Team
The team has just completed a very successful Sprint Review and is proud of the increment they've produced. The Development Team is highly motivated to work on related material that the Review did not prioritize and asks you to reprioritize the Product Backlog so they can they can finish up the features they'd just done so well on.
How do you respond?

## Slide 56: Scheduling Conflict
The Scrum Master contacts you to let you know that the Development Team has discovered that it underestimated the work for the current Sprint. They would like you to come in the next morning to discuss necessary modification. You have a long-scheduled meeting that morning to present a project proposal that could generate millions in revenue.
What do you do?

## Slide 57: Technical Product Owner
You're an experienced expert in a technology being used on the product under development and have occasionally mentored the development team on some more advanced topics. The development team has learned that your main project is wrapping up and has invited you to join them on this one, arguing that you can both contribute more with your expertise and be a better product owner if you're there all the time. How do you respond?

## Slide 58: Contracted Product Owner
You've been brought in by a client to serve as Product Owner for a project being developed by your company as well. Prior to the last Sprint before a decision is made on renewing your company's contract, the development team lets you know that there's a relatively valuable epic on the product backlog that they could do an astonishingly good job on and that one group of stakeholders has been clambering for. Based on your understanding of the business needs, however, you'd be hard pressed to consider it among the top five most valuable.
How do you respond?

## Slide 59: Embrace Change?
Your product is a week into it's 4-week development cycle of 3rd sprint when the chief marketing officer rushes into your office and announces that a certain feature needs to be implemented as quickly as possible in order to avoid serious negative press in a new market where this feature is considered essential. How do you respond?

## Slide 60: Flood of Change
It's now a week into the 8th sprint and the CMO is in your office for the 3rd time with a legitimately urgent need due to the rapid adoption of the product across the world.
What should be done to mitigate or eliminate the need to address these issues over and over?
(This is ultimately not your decision, but you're the one in the hot seat and should be open with recommendations.)

## Slide 61: Overactive Product Owner
As product owner, you're responsible for being available to the development team. For several sprints now you have found yourself working with them several times a week to clarify requirements they're working on. What might have caused this and how can it be corrected?